## Process
Step | sub step | sub step | ref | Status | Dependencies | Notes
Download MongoDb |  |  | https://www.mongodb.com/try/download/community | WIP |  | Reboot reqd
Setup a free AWS instance using Mongo Db |  |  | Getting Started with AWS and MongoDb | WIP |  | Await completion email Problem My account exists/does not exist at the same time - contacted support await reply
Setup the MongoDb Cloud |  |  |  | WIP
Install MongoDbShell |  |  |  | COMPLETE |  | v 1.8.0 Windows
Using AWS Lambda with Amazon S3 |  |  | https://docs.aws.amazon.com/lambda/latest/dg/with-s3.html | HOLD | Setup a free AWS instance using Mongo Db | Issue with AWS Login - await resolution
Using AWS Lambda with Amazon S3 Create a web API with ASP.NET Core and MongoDB |  |  |  | WIP
| Configure MongoDB |  |  | WIP
|  | mongod --dbpath "D:\Data\Family\Terry\Jobs\Ash Ali and Nasim Ghouri CoreThree\Solution\Data" |  | COMPLETE
|  | mongosh |  | COMPLETE
|  | create CoreThree db and use |  | COMPLETE |  | this created the new db and set it as the context db
|  | Create a Books collection called 'Tickets' | db.createCollection('Tickets') | COMPLETE |  | Colllection xists
|  | Define a schema for the Tickets collection and insert two documents | db.Tickets.insertMany([{ "type": "Flight", "Depart": "02-FEB-2023 2145", "ETA": "03-FEB-2023 1920", "carrierId": "Emirates", "start_node": "LHR", "end_node": "DVO", "route":"LHR-DXB,DXB-MNL,MNL-DVO", "price": "2040.45", "currency": "GBP", "status": "Paid", "agency": "Scammer Travel", "agent":"Natalie Hawkins 506", "customerId":"John H Barton 331", "documentStatus":"Checked", "specialRequirements":"Plenty beer", "notes":"Bad tempered client", "luggage":"Hold 2 50 Cabin 1 7" } , { "type": "Bus", "Depart": "09-MAR-2023 0910" "ETA": "09-MAR-2023 0900" "carrierId": "Quantum Entanglement Co", "start_node": "Luton Central", "end_node": "Heaven, Main", "route":"LUTM-HVNM", "price": "5100.45", "currency": "USD", "status": "Quote", "agency": "Faster than Light Travel", "agent":"Grim reaper 2", "customerId":"Fallen Angel 1", "documentStatus":"Checked", "specialRequirements":"Harp", "notes":"Brused ass when hit ground","luggage":"" }]) | COMPLETE |  | chkd 2 records
| Create a MongoDB database |  |  | COMPLETE
| Define a MongoDB collection and schema |  |  | COMPLETE
Create the ASP.NET Core web API project | Create a ASP.NET Core Web API | named CoreThree net 6. |  | COMPLETE
| install the .NET driver for MongoD |  |  | COMPLETE
| Add the Ticket entity model | crt Models folder and the ticket the poco class |  | COMPLETE
| add config |  |  | COMPLETE
|  | { "BookStoreDatabase": { "ConnectionString": "mongodb://localhost:27017", "DatabaseName": "Core3", "BooksCollectionName": "Tickets" }, "Logging": { "LogLevel": { "Default": "Information", "Microsoft.AspNetCore": "Warning" } }, "AllowedHosts": "*" } |  | COMPLETE
|  | CoreThreeDatabaseSettings class: namespace CoreThree.Models; public class CoreThreeDatabaseSettings { public string ConnectionString { get; set; } = null!; public string DatabaseName { get; set; } = null!; public string TicketsCollectionName { get; set; } = null!; } |  | COMPLETE
|  | Program.cs:var builder = WebApplication.CreateBuilder(args);// Add services to the container. builder.Services.Configure<BookStoreDatabaseSettings>( builder.Configuration.GetSection("BookStoreDatabase")); |  | COMPLETE
|  | Program.cs:var builder = WebApplication.CreateBuilder(args);// Add services to the container. builder.Services.Configure<BookStoreDatabaseSettings>( builder.Configuration.GetSection("BookStoreDatabase")); |  | COMPLETE
using Core3Api.Models;
| Add a CRUD operations service | Create the service class to do the Crud called CoreThreeService |  | COMPLETE
| Program.cs: | … |  | COMPLETE
| TicketsController : ConntrollerBase the 5 crud ops | GetAll |  | COMPLETE
|  | Get (one) |  | COMPLETE
|  | Create (Post) |  | COMPLETE
|  | Update (put) |  | COMPLETE
|  | Delete |  | COMPLETE
| Tested - smple Swagger UI crud tests |  |  | PASSED

## Lists
STATUS
OS
WIP
HOLD
COMPLETE
FAILED
PASSED